## Executive Summary
AMUSEMENT RIDE CRM & INVENTORY SYSTEM
Technical Scope Work Estimation & Project Execution Metrics (.NET 8 Razor Pages)
| TOTAL PROJECT EFFORT |  | CALENDAR DURATION |  | CORE FEATURE MODULES |  | SPECIALIST TEAM SIZE
| 1,088 Hours |  | 13.6 Weeks (~3.5 Mo) |  | 14 Modules |  | 4 Resources
1. Effort Distribution by Engineering Discipline
| Discipline | Effort (Hours) | % of Total | Primary Tech Stack / Tools | Assigned Role
| Database Architecture & EF Core 8.0 |  |  | SQL Server, EF Core 8.0, Migrations, RowVersion | Lead Architect / Senior Backend
| Backend Business Logic, Services & Handlers |  |  | C# 12, ASP.NET Core 8.0, QBWC SOAP, Polly | Senior Full-Stack Developers (x2)
| Frontend UI, Razor Pages & Bootstrap 5.3 |  |  | Razor Pages (.cshtml), Bootstrap 5.3, Bootstrap Icons | Full-Stack / UI Developers
| Quality Assurance, Unit & E2E Integration Testing |  |  | xUnit, Moq, Testcontainers, Selenium/Playwright | QA Automation Engineer / Team
| Total Estimated Effort |  |  | All Technical Layers | 4 Core Team Members
2. Phased Milestone Execution Schedule
| Phase | Milestone Focus | Target Duration | Total Hours | % Total | Key Deliverables
| Phase 1 | Foundation, Master Data & Part Merging | Weeks 1 - 3 | 200 |  | Schema, Auth, Customers, Rides, Multi-Vendor Parts, Part Merge Tool
| Phase 2 | Customer Quotes, Orders & Inventory Reservations | Weeks 4 - 6 | 244 |  | Quote workflow, Markup formula, Order lifecycle, Holding bin engine
| Phase 3 | Purchasing Queue, POs, AI Invoices & Receiving | Weeks 7 - 9 | 336 |  | Demand consolidation, Vendor POs, Document AI review, ZPL label printing
| Phase 4 | Shipping Management & UPS REST Integration | Weeks 10 - 11 | 88 |  | Complete/Partial shipping, Holding release, UPS live rating & label generation
| Phase 5 | Customer Invoicing & QuickBooks Desktop Sync | Weeks 12 - 13 | 168 |  | Billing queue, QBWC SOAP Bridge, qbXML customer/invoice/bill sync
| Phase 6 | End-to-End Hardening, User Acceptance & Launch | Week 14 | 52 |  | Full integrated scenario testing, Pilot data sync, Go-live deployment
| Total | Complete Scope Delivery | 14 Calendar Weeks |  |  | Full Production Readiness

## Granular Breakdown
GRANULAR TASK & WORK ESTIMATION BREAKDOWN
Detailed Breakdown by Feature Module, Technical Layer and Task Scope
ID | Feature Module | Functional Scope & Deliverables | DB / EF Core (Hrs) | Backend Logic (Hrs) | Frontend UI (Hrs) | Testing & QA (Hrs) | Total Module Hours
MOD-01 | 1. Foundation, Identity & Data Layer | EF Core 8.0 schema, AuditableEntity base classes, Identity RBAC (Admin, Office, Buyer, Warehouse, Accounting), User management Razor Pages | 18 | 20 | 14 | 12
MOD-02 | 2. Customer & Ride Tracking | Customer master (QB sync flag), Multi-contact management, Customer rides (Manufacturer, Model, Serial #), Ride selector component | 8 | 14 | 16 | 10
MOD-03 | 3. Inventory Master & Part Merge Tool | Multi-vendor sources (EUR cost, lowest cost default), Ride applications, Non-stocked part flags, Duplicate part merge wizard with audit history | 16 | 28 | 22 | 18
MOD-04 | 4. Customer Quotes & Dynamic Pricing | Configurable EUR factor & Markup, Quote creation, PDF terms generation, Expiration dates, 1-click conversion to Customer Order | 10 | 24 | 20 | 14
MOD-05 | 5. Customer Orders & Holding Bins | Order workflow (Quote -> Shipped), Complete vs Partial shipment flags, Order holding location allocation, Manual price & charge adjustments | 14 | 32 | 26 | 20
MOD-06 | 6. Inventory Reservation Engine | Real-time state machine: Available = QOH - Reserved, Optimistic concurrency (RowVersion), Atomic stock locking, Deficit routing to queue | 12 | 36 | 12 | 24
MOD-07 | 7. Purchasing Queue & Aggregation | Demand aggregation from order deficits & ROP triggers, Consolidate by Vendor + Ride, Source order traceability, Manual qty adjustments | 12 | 34 | 24 | 18
MOD-08 | 8. Purchase Order Management | PO generation in EUR, Ride/Serial display for vendor verification, PO editing post-dispatch, Order line purpose retention (demand vs stock) | 10 | 22 | 20 | 12
MOD-09 | 9. AI Vendor Invoice Processing | Azure Document Intelligence / Vision API integration, Split-screen PDF extraction UI, Part cross-referencing, Master cost updates & open order alerts | 10 | 38 | 32 | 22
MOD-10 | 10. Warehouse Receiving & Labels | PO line receiving, Partial receipt tracking, Over-delivery warning gates, Auto-reservation & holding directives, ZPL thermal barcode label printing | 12 | 28 | 24 | 18
MOD-11 | 11. Shipping & UPS REST API | Complete vs Partial fulfillment dashboard, Pick lists from warehouse & holding bins, UPS REST API (Rating, Shipping labels, Tracking #), Manual override | 10 | 34 | 24 | 20
MOD-12 | 12. Customer Invoicing Queue | Post-shipment billing queue, Multiple shipments -> multiple invoices, Additional charges (shipping, rush fee, discount), Manual review approval | 8 | 18 | 16 | 12
MOD-13 | 13. QuickBooks Desktop Sync (QBWC) | Isolated sync bridge, SoapCore QBWC endpoint, qbXML Customer/Invoice/Bill generation, Transaction ID retention & idempotency guarantees | 16 | 48 | 22 | 28
MOD-14 | 14. Audit Trail, Dashboard & Settings | Operational command center, Price change discrepancy alerts, Configuration page (EUR factor, markup), Complete transaction audit history | 8 | 18 | 18 | 12
TOTAL | All 14 Project Modules | Complete ASP.NET Core 8.0 Razor Pages Execution

## Staffing & Schedule
RESOURCE STAFFING PLAN & 14-WEEK ALLOCATION
Weekly Capacity Allocation per Specialist Resource
Resource Role | Focus & Core Responsibilities | Weekly Hours | Total Hours | Allocation % | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Lead Architect / Tech Lead | Architecture, QBWC SOAP Bridge, Concurrency, Security, Code Reviews | 18 |  | 45% | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Senior Full-Stack Dev 1 | EF Core Models, Reservation Engine, Orders, Purchasing Queue, Receiving | 35 |  | 87.5% | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
Senior Full-Stack Dev 2 | AI Document Extraction, Razor Pages UI, UPS API, Invoicing, Labels | 35 |  | 87.5% | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
QA & Automation Engineer | Test Plans, Integration Tests, QB Synchronization Verification, UAT | 16 |  | 40% | 12 | 12 | 14 | 14 | 16 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 20 | 20
TOTAL TEAM VELOCITY | Blended Engineering Velocity (Hrs/Wk) |  |  | 100% Blended

## Assumptions & Risks
PROJECT ASSUMPTIONS & RISK MITIGATION REGISTER
Technical Preconditions, External Constraints, and Risk Management
1. Technical & Architectural Assumptions
ID | Domain Area | Assumption Description | Impact if Invalidated
ASM-01 | QuickBooks Desktop | Client operates a supported QuickBooks Desktop Enterprise / Premier version and provides a sanitized .QBW company file for local development & staging. | High: Delays in sync development if QB Desktop instance cannot be tested locally.
ASM-02 | QBWC Integration Protocol | Sync is implemented using the standard QuickBooks Web Connector (QBWC) SOAP protocol. PO sync is excluded from Phase 1 per scope §20. | Medium: Custom Windows COM service would require additional development hours.
ASM-03 | Document AI Service | Scanned vendor invoices are at least 200 DPI resolution, and client provisions an Azure Document Intelligence or OpenAI Vision API subscription. | High: Poor OCR quality requires more manual human data entry.
ASM-04 | Zebra / Thermal Hardware | Warehouse label printers support raw ZPL over TCP/IP (port 9100) or standard Windows network print spooling. | Low: PDF fallback printing will be available through the browser.
ASM-05 | Pricing Formula & Currency | Vendor invoices are in Euros (EUR). Master conversion factor and markup remain system-wide configurable. Inbound freight is not allocated to unit cost. | Medium: Per-part freight allocation would require complex cost accounting adjustments.
ASM-06 | Out-of-Scope Confirmation | CRM/ACT sync, AI photo part recognition, mobile Zebra handheld apps, and automatic email dispatch are confirmed as Phase 2 items (§25). | High: Introducing mobile apps or CRM in Phase 1 would expand scope significantly.
2. Technical Risk Management Register
Risk ID | Risk Description | Severity | Probability | Impact Assessment | Architectural Mitigation Strategy
RSK-01 | QuickBooks Desktop Web Connector concurrency locks or transaction timeouts during simultaneous polling. | High | High | Sync queue blocks or creates partial records in QB. | Implement sequential database queue with atomic lock (sp_getapplock). Store QB TxnID immediately to ensure idempotency.
RSK-02 | Inventory race conditions when multiple office users confirm orders for identical stock simultaneously. | High | Medium | Inventory oversold resulting in unfulfilled customer orders. | Apply EF Core optimistic concurrency ([Timestamp] RowVersion) on Part entity with Serializable database transactions.
RSK-03 | Vendor invoice AI extraction errors on complex or irregular European invoice formats. | Medium | High | Incorrect part matching or erroneous EUR costs saved. | Strict Human-in-the-Loop review: split-screen UI requires manual confirmation before saving to master part or QB Bill queue.
RSK-04 | Vendor cost increases on parts for orders already confirmed with customers. | Medium | High | Profit margin erosion or customer billing disputes. | System recalculates future selling prices but explicitly flags open customer orders for manual review without auto-changing prices.
RSK-05 | UPS Carrier API rate limits or intermittent network outages at shipping docks. | Low | Medium | Warehouse shipping operations temporarily blocked. | Built-in manual override allows warehouse personnel to enter tracking numbers and shipping costs manually.
RSK-06 | QuickBooks company file schema discrepancies between test file and live production company file. | High | Low | QBWC SOAP fails to locate required Chart of Accounts or Items. | Dedicated pre-launch verification script validates all Account Names, Tax Codes, and Item Masters against live QB Desktop prior to cutover.